## Project Profile
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | PRJ_OnlineAirlineBooking_001
Project Name | FlyWithMe Online Airline Booking System
Prepared/Modified by | Role | Date of Preparation
Reviewed by | Role | Date of Review
Approved by | Role | Date of Approval
Circulation List
Version Number

## Defect Tracking Sheet
Project ID: | PRJ_OnlineAirlineBooking_001 | Project Name : | FlyWithMe Online Airline Booking System | [22 empty] | VERIFIED
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachments | Comments |  | REOPENED | Coding |  |  | Internal Dev
DF_ADMIN_001 | Authority Login | The admin username field in the authority login page is found to accept invalid value. | Detailed Description: The admin enters the invalid value in the username field in the authority login page of the application.The username field is found to accept invalid value. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Select Role. 5. Enter invalid username 6. Enter valid password. 7. Click on login. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts invalid value in the admin username field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_ ADMIN_003 | [8 empty] | PPR | ACT | Enhancement | P1 | Medium | External Dev
DF_ADMIN_002 | Authority Login | The admin password field in the login page is found to accept invalid value. | Detailed Description: The admin enters the invalid value in the password field in the authority login page of the application.The password field is found to accept invalid value. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Select Role. 5. Enter invalid username 6. Enter valid password. 7. Click on login. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts the invalid value in the password field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_ ADMIN_005
DF_ADMIN_003 | Authority Login | The admin logs into the authority login page of appilication with out selecting the role. | Detailed Description:The authority person logs into the authority login page of the appilication with out selecting the role .The error message is displayed to select the role. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Select Role. 5. Enter invalid username 6. Enter valid password. 7. Click on login. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts invalid selection of the role.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_ ADMIN_008 | [8 empty] | UTC |  | Master Data | Medium
DF_ADMIN_004 | Authority Login | The admin username field and password field in the login page is found to accept null values. | Detailed Description: The admin enters null values in username field and the password field in the authority login page of the application.The username field and password field is found to accept null values and admin is redirecting to next page of the appilication without getting any error message. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Select Role. 5. Enter invalid username 6. Enter valid password. 7. Click on login. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts the null value in the username field and null value in the password field .The application navigates to next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_ ADMIN_010
DF_EXCEUTIVE_005 | Authority Login | The exceutive username field in the login page is found to accept invalid value. | Detailed Description: The exceutive enters the invalid value in the username field in the authority login page of the application.The username is found to accept the invalid value. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Select Role. 5. Enter invalid username 6. Enter valid password. 7. Click on login. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts the invalid value in the username field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_ EXCEUTIVE_013
DF_EXCEUTIVE_006 | Authority Login | The exceutive password field in the login page is found to accept invalid value. | Detailed Description: The exceutive enters the invalid value in the password field in the authority login page of the application.The password is found to accept the invalid value. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Select Role. 5. Enter invalid username 6. Enter valid password. 7. Click on login. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts the invalid value in the password field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_ EXCEUTIVE_015
DF_EXCEUTIVE_007 | Authority Login | The exective logs into the authority login page of appilication with out selecting the role. | Detailed Description: The exceutive enters the username field and the password field in the authority login page of the application with out selecting the role. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Select Role. 5. Enter invalid username 6. Enter valid password. 7. Click on login. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts the invalid value in the username field and invalid value in the password field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_ EXCEUTIVE_018
DF_EXCEUTIVE_008 | Authority Login | The exceutive username field, password field and role in the login page is found to accept null value. | Detailed Description: The exceutive enters null username field and the password field in the authority login page of the application.The username field and password field is found to accept null values and exceutive is navigating to next page of the appilication without getting any error message. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Select Role. 5. Enter invalid username 6. Enter valid password. 7. Click on login. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts the null value in the username field and null value in the password field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_ EXCEUTIVE_020
DF_BOOK_A_TICKET_009 | Book A Ticket page validation. | The type of class field in the book your ticket page is found to accept null value. | Detailed Description: The user enters the number of passengers field and doesnt select the class and clicks on the submit in the give your choice page of the application.The number of passengers field and class field is found to accept valid values and user should navigates to next page without getting any error message. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Select View Flights. 4. Click on book for corresponding flight. 5. Enter Number of Passengers. 6. Select class 6. Click on submit. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts the valid value in the number of passengers field and invalid value in the class field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_BOOK_A_TICKET_024
DF_BOOK_A_TICKET_010 | Book A Ticket page validation. | The number of passengers field in the book your ticket page is found to accept invalid value. | Detailed Description: The user enters negative number in number of passengers field and selects the class and clicks on the submit in the give your choice page of the application.The number of passengers field and class field is found to accept negative values and user should navigates to next page without getting any error message. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Select View Flights. 4. Click on book for corresponding flight. 5. Enter Number of Passengers. 6. Select class 6. Click on submit. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts the invalid value in the number of passengers field and valid value in the class field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_BOOK_A_TICKET_026
DF_BOOK_A_TICKET_011 | Book A Ticket page validation. | The number of passengers field and type of class field in the book your ticket page is found to accept null values. | Detailed Description: The user enters null value in number of passengers field and doesnot selects the class and clicks on the submit in the give your choice page of the application.The number of passengers field and class field is found to accept null values and user navigates to next page without getting any error message. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Select View Flights. 4. Click on book for corresponding flight. 5. Enter Number of Passengers. 6. Select class 6. Click on submit. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts the null value in the number of passengers field and null value in the class field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Google Chrome | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_BOOK_A_TICKET_029
DF_ BOOKING INFORMATION_012 | Booking information validation | The name field in the booking information page is found to accept null value. | Detailed Description: The user enters null value in nameof the passenger field and enters valid email id and clicks on the submit in the booking information page of the application.The name of the passenger field is found to accept null values and user navigates to next page without getting any error message. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Select available Flights page. 4. Click on give your choice page. 5. Enter number of passengers 6.Enter class 7. click on submit button 8.Click on confirm button in the your journey details page. 9. Enter name of passenger. 10. Enter email id 11. Click on make reservation. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application navigates to next page.There is no error message shown. | Coding | Google Chrome | Internal Dev | P1 | high | 1.3.4 | 4 | [5 empty] | TC_ARS_BOOKING_INFORMATION_035
DF_ BOOKING INFORMATION_013 | Booking information validation | The email field in the booking information page is found to accept invalid value. | Detailed Description: The user enters valid value in nameof the passenger field and enters invalid email id and clicks on the submit in the booking information page of the application.The email field is found to accept invalid value and user navigates to next page without getting any error message. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Select available Flights page. 4. Click on give your choice page. 5. Enter number of passengers 6.Enter class 7. click on submit button 8.Click on confirm button in the your journey details page. 9. Enter name of passenger. 10. Enter invalid email id 11. Click on make reservation. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application navigates to next page.There is no error message shown. | Coding | Google Chrome | Internal Dev | P1 | high | 1.3.4 | 4 | [5 empty] | TC_ARS_BOOKING_INFORMATION_036
DF_ BOOKING INFORMATION_014 | Booking information validation | The email field and the name of the passenger field in the booking information page is found to accept null values. | Detailed Description: The user enters null value in nameof the passenger field and in email id field and clicks on the submit in the booking information page of the application.The name of the passenger field and email field is found to accept null value and user navigates to next page without getting any error message. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Select available Flights page. 4. Click on give your choice page. 5. Enter number of passengers 6.Enter class 7. click on submit button 8.Click on confirm button in the your journey details page. 9. Enter null name of passenger. 10. Enter null email id 11. Click on make reservation. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application navigates to next page.There is no error message shown. | Coding | Google Chrome | Internal Dev | P1 | high | 1.3.4 | 4 | [5 empty] | TC_ARS_BOOKING_INFORMATION_038
DF_ARS_PAYMENT _015 | Payment page validation | The card details field is found to accept null values in the payment page. | Detailed Description: The user enters null value in card details field and selects a valid payment type and clicks on make payment button in the payment page of the application.The card details field is found to accept null value and user navigates to next page without getting any error message. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Select available Flights page. 4. Click on give your choice page. 5. Enter number of passengers 6.Enter class 7. click on submit button 8.Click on confirm button in the your journey details page. 9. Enter name of passenger. 10.Enter emailid 11.Click on the make reservation in booking information page. 12.Select type of payment. 13.Enter valid card details. 14.Click on make payment Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application navigates next page .There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | high | 1.3.4 | 4 | [5 empty] | TC_ARS_PAYMENT_044
DF_ARS_BOOK_FLIGHT _016 | Book Flights | The number of passenger field in the Book Flights is found to accept negative values. | Detailed Description: The user enters the negative value in the number of passengers field of book fligths page of the application.The number of passengers Fields are found to accept negative value. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on BookFligths link 4. Enter combination in To and From fields 5. Enter the departure date 6. Enter the invalid number of passengers 7.Select the Class 8.Click on serach Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts invalid number of travelles field.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | high | 1.3.4 | 4 | [5 empty] | TC_ARS_BOOK_FLIGHT_053
DF_ARS_BOOK_FLIGHT _017 | Book Flights | The departure date field in the bookflights field is found to accept null date | Detailed Description: The user enters the invalid value in the depature date field of book fligths page of the application.The depature date field is found to accept negative value. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on BookFlights link 4. Enter valid combination in To and From fields 5. Enter invalid departure date 6. Enter the valid number of passengers 7.Select the class 8.Click on Search Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts invalid value in the departure date field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_BOOK_FLIGHT_052
DF_ARS_CONTACT US _018 | Contact Us | The name field in the Contact Us page is found to accept null values. | Detailed Description: While Putting a query in Contact Us page ,when user leaves the name field empty but enters the valid values in email,message fields, the application allows user to submit the query instead of showing appropriate error message. Steps to produce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Contact Us link 4. Leave name field blank 5. Enter valid email Id 6.Enter Message 7. Click on Send Message. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts null values in the name field and the application accepts the query.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_CONTACT_US_059
DF_ARS_CONTACT US _019 | Contact Us | The email id field in the Contact Us page is found to accept invalid format | Detailed Description: While Putting a query in Contact Us page ,when user enters the invalid format of emaild field, the application allows user to submit the query instead of showing appropriate error message. Steps to produce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Contact Us link 4. Leave name field blank 5. Enter valid email Id 6.Enter Message 7. Click on Send Message. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts null values in the name field and the application accepts the query.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.3.4 | 4 | [5 empty] | TC_ARS_CONTACT_US_063
Note on A2: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B2: Alphy Chenganiyadan: Give the name of the module being tested
Note on C2: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D2: Alphy Chenganiyadan: A detailed description of the defect
Note on E2: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F2: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G2: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H2: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I2: Prioritize the defect
Note on J2: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K2: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L2: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M2: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N2: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O2: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P2: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q2: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R2: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S2: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T2: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U2: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V2: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W2: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X2: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y2: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.

## Revision History
REVISION HISTORY OF WORK PRODUCT (to be maintained by projects)
# | Date | Version # | Section Changed | Details of changes made | Approved By